## Pre-Production Checklist
Salesforce CRM — Pre-Production Deployment Checklist
Sciagen CRM · Dedicated Production Org Go-Live — complete before the production deployment window
# | Checklist Item | Owner | Status | Target Date | Notes
1. Environment & Org Setup
1 | Dedicated production org provisioned and confirmed (edition, storage, user licenses match contract) | Kesav | Done | 18/09/2026
2 | My Domain configured and deployed on the production org | Kesav | In Progress | 21/09/2026
3 | Company information, business hours, and fiscal year settings configured | Kesav | In Progress | 21/092026 | Done in Sanbox
4 | Login IP ranges / trusted IP ranges configured for org and profiles | Vivek | N/A
5 | Multi-Factor Authentication (MFA) enabled and enforced for all users (Salesforce mandatory requirement) | Kesav | In Progress | 18/09/2026
6 | Password policies and session timeout settings configured to org standards | Kesav | In Progress
7 | Deployment/Integration user created with a dedicated profile (not a named human user) | Kesav | Not Started |  | Done in Sandbox
8 | Sandbox refreshed from production (or newly created) to serve as the final pre-go-live staging environment | Kesav | Not Started
2. Salesforce Configuration
9 | Org-Wide Defaults (OWD) set for Sciagen_Account__c, Affiliation__c, Data_Change_Request__c, Planned_Call__c, Call_Visit_Report__c | Kesav | Done | 20/09/2026 | Done in Sandbox
10 | Role hierarchy and sharing rules configured and validated against the business territory/reporting model | Kesav | Not Started
11 | Profiles and Permission Sets finalized (Sales Rep, Data Steward/Admin, System Administrator) with least-privilege field-level security | Kesav | Done | 20/09/2026 | Done in Sandbox
12 | Record Types and Page Layouts assigned per profile (HCP vs HCO, New vs Edit DCR) | Kesav | Done | 20/09/2026 | Done in Sandbox
13 | Picklist values reconciled between Salesforce (HCO_Type__c, HCP_Type__c, Speciality__c/Specialty__c) and the iPad app's local option lists | Kesav | Done | 20/09/2026 | Done in Sandbox
14 | Validation rules reviewed and tested against real-world edge cases (blank/overlong values, special characters) | Kesav | Done | 20/09/2026 | Done in Sandbox
15 | Flows, Process Builders, and the DataChangeRequestTrigger/DataChangeRequestApprovalHandler reviewed as Active (not left in Draft) | Kesav | Done | 20/09/2026 | Done in Sandbox
16 | Email templates, notification templates, and org-wide email addresses configured and verified | Kesav | Done | 20/09/2026
17 | Custom Settings / Custom Metadata Types populated with production values (not sandbox/dev values) | Kesav | Done | 20/09/2026 | Done in Sandbox
18 | Duplicate & Matching Rules configured for Sciagen_Account__c (HCP/HCO) to prevent duplicate master data | Kesav | Done | 20/09/2026 | Done in Sandbox
19 | Reports & Dashboards folder structure and sharing set up for go-live | Kesav | Done | 20/09/2026
3. Code & Metadata Readiness
20 | Full regression of the SFDX metadata deployed and validated in a full-copy sandbox first (not production directly) |  | Not Started | 23/09/2026
21 | Org-wide Apex test coverage ≥75%, with all DCR/CVR/Account-critical classes individually covered |  | Not Started
22 | DataChangeRequestApprovalHandlerTest and related Apex tests passing with 0 failures |  | Not Started
23 | No hardcoded sandbox URLs, sandbox-only record Ids, or sandbox Named Credentials left in Apex/LWC code |  | Not Started
24 | Remote Site Settings and Named Credentials re-pointed to production endpoints |  | Not Started
25 | Static code review / PMD scan completed with no critical/high findings outstanding |  | Not Started
26 | Deployment package (package.xml or SFDX source list) finalized and peer-reviewed |  | Not Started
27 | Deployment method and sequence confirmed (SFDX project deploy / CI-CD pipeline), including dependency order |  | Not Started
4. Data Migration Readiness
28 | Data migration plan and field-mapping document finalized and signed off (source system -> Sciagen_Account__c / Affiliation__c) |  | N/A
29 | Source data cleansed and normalized (HCO/HCP Type, Speciality values mapped to Salesforce's valid picklist sets) |  | Not Started
30 | De-duplication strategy applied to source HCP/HCO records before load |  | Not Started
31 | Every HCP's affiliations reviewed so exactly one Is_Primary__c = true relationship exists per HCP |  | Not Started
32 | Data volumes estimated and checked against org storage limits and API call limits for the planned load |  | Not Started
33 | ETL/load tool selected and configured (Data Loader / Data Import Wizard / custom script) |  | Not Started
34 | Trial data migration executed end-to-end in the full-copy sandbox using production-representative volumes |  | Not Started
35 | Post-load validation queries/scripts prepared (row counts, required-field completeness, relationship integrity) |  | Not Started
36 | PII handling for HCP personal data (name, email, phone) reviewed for compliance before load |  | Not Started
37 | Backup/export of any pre-existing production org data taken before migration begins (rollback safety net) |  | Not Started
5. Integration Readiness (iPad App <-> Salesforce)
38 | Connected App created in production with its own OAuth Consumer Key/Secret (not reused from the dev org) |  | Not Started
39 | SciagenAccountSyncService REST endpoint (/sciagen/v1/accounts/*) tested end-to-end against the production URL |  | Not Started
40 | iPad app build configured/pointed at the production org's login/API host ahead of go-live |  | Not Started
41 | API version alignment confirmed between the iPad app's REST calls and the deployed Apex REST classes |  | Not Started
42 | OAuth scopes and refresh-token behavior tested for the field rep's typical multi-day session pattern |  | Not Started
43 | API usage/call volume estimated against the production org's daily API limit, including iPad autosync frequency |  | Not Started
6. Testing & Business Sign-off
44 | UAT completed in the full-copy sandbox with real business stakeholders and real-world scenarios |  | Not Started
45 | Critical journeys tested: DCR submission -> steward approval -> Account/Affiliation sync -> iPad autosync pickup |  | Not Started
46 | Critical journeys tested: Account Plan -> Planned Call -> Call Visit Report linking and 'View Call Report' navigation |  | Not Started
47 | Critical journeys tested: CVR/CLM presentation flow, internal attendee selection, consent handling |  | Not Started
48 | All P1/P2 defects from UAT closed or explicitly accepted/deferred with business sign-off |  | Not Started
49 | Formal Go-Live sign-off obtained from business/project sponsor |  | Not Started
7. Deployment Planning & Change Management
50 | Deployment window scheduled during a low-traffic/maintenance period and communicated to stakeholders |  | Not Started
51 | Go/No-Go readiness meeting held with all workstream owners (Salesforce, iPad app, data migration) |  | Not Started
52 | Rollback plan documented for both the metadata deployment and the data migration |  | Not Started
53 | Release notes and end-user training materials prepared and distributed ahead of go-live |  | Not Started
54 | Support/helpdesk process and escalation path defined for go-live day |  | Not Started

## Post-Production Checklist
Salesforce CRM — Post-Production Deployment Checklist
Sciagen CRM · Dedicated Production Org Go-Live — complete after the production deployment window
# | Checklist Item | Owner | Status | Target Date | Notes
1. Deployment Verification
1 | Metadata deployment to production completed with 0 component errors |  | Not Started
2 | All Apex tests ran as part of the production deployment and passed with 0 failures |  | Not Started
3 | Org-wide Apex code coverage confirmed ≥75% in production |  | Not Started
4 | Triggers (DataChangeRequestTrigger), Flows, and scheduled jobs confirmed Active in production |  | Not Started
5 | Custom Settings / Custom Metadata Type values spot-checked in production for correct (non-dev) values |  | Not Started
6 | Page layouts, record types, and permission sets confirmed visible/assigned correctly for a sample user per profile |  | Not Started
2. Data Migration Verification
7 | Migrated record counts reconciled against source system counts (Sciagen_Account__c, Affiliation__c, etc.) |  | Not Started
8 | Spot-check sample of migrated HCP/HCO records for field-level accuracy against source data |  | Not Started
9 | Every migrated HCP confirmed to have exactly one primary (Is_Primary__c = true) Affiliation__c |  | Not Started
10 | No duplicate Sciagen_Account__c records introduced by the migration (duplicate rule / manual scan) |  | Not Started
11 | Any temporary/test/dummy records used during migration rehearsal purged from production |  | Not Started
12 | Data migration exception/error log reviewed and all exceptions resolved or explicitly accepted |  | Not Started
3. Security & Access Verification
13 | All go-live users provisioned with the correct Profile/Permission Set combination |  | Not Started
14 | MFA enforcement confirmed active for all production users |  | Not Started
15 | Field-level security spot-checked for sensitive fields (HCP contact details) across each profile |  | Not Started
16 | Sharing model validated with a 'login as' / test-user check for at least one record per role |  | Not Started
17 | Login history and audit trail (Setup Audit Trail) confirmed enabled and capturing events |  | Not Started
4. Integration Verification
18 | iPad app successfully authenticates against the production org (OAuth login smoke test) |  | Not Started
19 | End-to-end smoke test: submit a real Edit/New HCP or HCO DCR from the iPad app |  | Not Started
20 | End-to-end smoke test: steward approves the DCR in the DCR Review queue and the Account/Affiliation updates correctly |  | Not Started
21 | End-to-end smoke test: iPad app's next autosync cycle picks up the approved change |  | Not Started
22 | API usage dashboard checked for unexpected call volume or errors in the first 24-48 hours |  | Not Started
5. Monitoring & Hypercare
23 | Debug logs / Apex exception email alerts enabled for the hypercare window |  | Not Started
24 | Hypercare support period defined (e.g., 1-2 weeks of elevated support coverage) and staffed |  | Not Started
25 | Storage and API limit dashboards checked daily during hypercare |  | Not Started
26 | Any production incidents logged with root cause and resolution |  | Not Started
6. Documentation & Handover
27 | Deployment record documented: what was deployed, when, by whom, and the deployment/job Id |  | Not Started
28 | Data dictionary and technical documentation updated to reflect the final production configuration |  | Not Started
29 | Admin runbook (common tasks, DCR approval process, troubleshooting) handed over to the client's Salesforce admin |  | Not Started
30 | Training materials and release notes distributed to end users |  | Not Started
31 | Outstanding known issues / backlog items logged in the tracking system for future iterations |  | Not Started
7. Closure & Sign-off
32 | Post-deployment validation formally signed off by the business/project sponsor |  | Not Started
33 | Go-live communication sent to all stakeholders confirming successful production launch |  | Not Started
34 | Project retrospective / lessons-learned session scheduled |  | Not Started