## Checklist
Sciagen CRM - Production Deployment Checklist
Fill in Status, Owner, Date done and Notes (yellow columns). "Project-specific" items come from issues found in devorg1, Int and the iPad sync.
# | Phase | Checklist item | How to verify / detail | Type | Status | Owner | Date done | Notes
1 | A. Pre-deployment gate | Run all local tests on the exact deployment package | A production deploy runs every local test and all must pass. Known open failure: DeviceResetVerifyApiTest.repPermissionSetCannotReadTheCode (reps can still read the device-reset OTP; the current iPad build depends on it). Either wait for the iPad change + FLS removal, or deploy with a specified test list that excludes it. | Project-specific | Not started
2 | A. Pre-deployment gate | Confirm every Apex class has at least 75% coverage (team target 80%) | Last clean run in devorg1: 173 classes, none below 80%, org-wide 94%. Re-check on the final package. | General | Not started
3 | A. Pre-deployment gate | Validate first (check-only deploy), then quick-deploy the validated package | sf project deploy start --dry-run ... then quick deploy from Setup > Deployment Status. | General | Not started
4 | A. Pre-deployment gate | Deploy from a fresh retrieve of devorg1 - not from the git repo | The repo has drifted. Old copies have overwritten fixes twice (AccountPlanController methods, the Accounts territory filter). Retrieve, diff, then deploy. | Project-specific | Not started
5 | A. Pre-deployment gate | Decide on the items excluded from the Int move | Sciagen_CRM app (Int has ~38 more nav tabs), Business Admin profile (devorg1 lower on 47 objects), Business_Admin_Full_Access (Int has 109 Acaroid FLS rows), ZZ_Probe_Type report type. Merge or leave - do not overwrite blindly. | Project-specific | Not started
6 | A. Pre-deployment gate | Remove test leftovers before packaging | ZZ_Probe_Type report type in devorg1; any ZZ* probe classes; test-only data. | Project-specific | Not started
7 | A. Pre-deployment gate | Back up production metadata | Retrieve the same package from production and keep it for rollback (include profiles, permission sets, layouts, app, sharing rules). | General | Not started
8 | A. Pre-deployment gate | Prepare the destructive-changes list (if any) | Components that must be deleted in prod (e.g. renamed classes). Confirm nothing in prod still references them. | General | Not started
9 | A. Pre-deployment gate | Choose the deployment window outside rep call hours | Warn users that iPad sync may pause briefly. Check whether any scheduled batch (license expiry, duplicate scan, purge) runs during the window. | General | Not started
10 | A. Pre-deployment gate | Review what changes for users on release day | The profile-to-permission-set automation will start assigning sets to every user created or changed in production. | Project-specific | Not started
11 | A. Pre-deployment gate | Get business and iPad-team sign-off on the release notes | Include new endpoints (team-schedule me/kams/calls/accounts/account-activity) and the device-reset verify endpoint for the app team. | General | Not started
12 | B. Immediately after deploy | Check Deployment Status: all components succeeded, 0 failures | Setup > Deployment Status; save the deploy ID in the release record. | General | Not started
13 | B. Immediately after deploy | Confirm no Apex class or trigger is invalid | Setup > Apex Classes: recompile all if needed. Pay attention to AccountPlanController, SupportUnlockService, SciagenAccountController. | Project-specific | Not started
14 | B. Immediately after deploy | Recreate scheduled jobs (they do not travel with a deployment) | HcpLicenseExpiryBatch, DuplicateScanScheduler, SyncTrackingPurgeJob, SampleLotExpiryBatch and any other Schedulable. Setup > Scheduled Jobs. | Project-specific | Not started
15 | B. Immediately after deploy | Verify Profile_Permission_Set_Map custom metadata records are active and correct | Manager: Manager Full Access, Mobile App Access, Reports User/Manager, Promotional Item Access, Acaroid Admin, Zonal Manager. KAM and Business Admin mappings likewise. | Project-specific | Not started
16 | B. Immediately after deploy | Assign permission sets to EXISTING users | The automation fires only on user create/update. Assign to current Managers, KAMs and Business Admins (bulk or script) and verify against one reference user. | Project-specific | Not started
17 | B. Immediately after deploy | Activate Lightning pages / app navigation where required | My Schedule page, Reports tab, Monthly Call Plans, Sciagen_CRM app nav. Check the app tab list against production before and after. | Project-specific | Not started
18 | B. Immediately after deploy | Verify page layout and record type assignments per profile | Presentation, Segmentation, Sciagen Account (HCP/HCO), Call Visit Report, Planned Call layouts. | General | Not started
19 | C. Org settings (not in deployment) | Set Email Deliverability to the required level | Setup > Deliverability (Access level: All email in production). Sent-email features and notifications depend on it. | Project-specific | Not started
20 | C. Org settings (not in deployment) | Review Sciagen_App_Config Default record values | Call day start/end hour, non-working days, lock segmentation on freeze, follow-up call hour, past-month freeze. devorg1 values differ from the code defaults. | Project-specific | Not started
21 | C. Org settings (not in deployment) | Review Sync_Object_Config__mdt rows | Every iPad object active with the right direction. The iPad shows "Sync pending" if this cannot be read. | Project-specific | Not started
22 | C. Org settings (not in deployment) | Set the Call_Backdate_Limit__c custom setting (org default) | The iPad reads it during sync; Managers need access through Sciagen_Mobile_App_Access. | Project-specific | Not started
23 | C. Org settings (not in deployment) | Configure external integrations | Geocoding API key (Geocoding_Config__mdt), S3 / CMS endpoints, remote site settings or named credentials, CMS push user and its permission set. | Project-specific | Not started
24 | C. Org settings (not in deployment) | Configure the iPad Connected App in production | Callback URL, OAuth scopes, IP relaxation, MFA / session policy, profile and permission-set access. | General | Not started
25 | C. Org settings (not in deployment) | Territory data | Territory hierarchy (Regions > Territories), User_Territory__c assignments, Account_Territory__c links; run a sharing recalculation if rules changed. | Project-specific | Not started
26 | C. Org settings (not in deployment) | Check picklist values and defaults | HCP Specialty / HCO Speciality (master-data list), HCO Type (incl. Private Clinic, Personal Clinic, Polyclinic), Training Type, Segmentation Classification V1/V2/V3, Slide File Type. | Project-specific | Not started
27 | C. Org settings (not in deployment) | Check custom permission grants | Support_Agent, Support_Unlock_Calls, Unlock_Monthly_Plans, Sciagen_Reports_Manager, Sciagen_Reports_Business_Admin are granted to the intended sets only. | Project-specific | Not started
28 | C. Org settings (not in deployment) | Check duplicate rules, validation rules and flows are active | Duplicate rules (3), approval processes (Device Reset, DCR), any flow in the package. | General | Not started
29 | D. Access verification (per role) | KAM: iPad login and Sync now shows "Connected" | No "Sync pending", no "account gateway sync error". Check Sync_Tracking__c for new Failed rows. | Project-specific | Not started
30 | D. Access verification (per role) | Manager: iPad sync, My Schedule KAM picker, DCR visibility | Manager Full Access, Zonal Manager Access and Mobile App Access must all be assigned. Sync_Object_Config__mdt must be readable. | Project-specific | Not started
31 | D. Access verification (per role) | Business Admin: Accounts page shows HCPs, HCOs and all territories | Business Admin is not a View-All-Data profile; the Accounts code treats it as admin explicitly. | Project-specific | Not started
32 | D. Access verification (per role) | System Admin: smoke test all admin pages | Reports admin, Duplicate Manager, Alert Admin, Sample Administration, Support Console. | General | Not started
33 | D. Access verification (per role) | Run the field-access check for every role against the iPad queries | All ~64 iPad queries in USER_MODE for each KAM / Manager / Business Admin - none may fail (catches missing FLS such as Acaroid fields). | Project-specific | Not started
34 | D. Access verification (per role) | Acaroid fields readable (about 100 on accounts, 7 on affiliations) | Granted by Sciagen_Acaroid_Admin; confirm it is assigned to every Manager and KAM. | Project-specific | Not started
35 | D. Access verification (per role) | Close the OTP exposure | Device_Reset_Request__c.OTP__c is readable (and editable) by KAM / Manager / Business Admin / Standard Platform User profiles. After the iPad uses the verify endpoint, remove read/edit for reps; keep Admin and approvers. | Project-specific | Not started
36 | D. Access verification (per role) | Review Business_Admin_Full_Access | In devorg1 and Int it has no object permissions, so Business Admins see data only through the role hierarchy. Decide the intended access and deploy it deliberately. | Project-specific | Not started
37 | D. Access verification (per role) | Review anything granting View All / Modify All | Mobile App permission set in the repo would add View All on 31 objects - do not deploy it without a security decision. | Project-specific | Not started
38 | E. Functional smoke tests | iPad: login, accounts list, account profile, tabs (Timeline, Segmentation, DCR) | As KAM and as Manager (including the KAM picker on Accounts and My Schedule). | General | Not started
39 | E. Functional smoke tests | iPad: schedule a call, open it, log and submit a call report | Check the follow-up call, check-in, signature, samples and key messages. | General | Not started
40 | E. Functional smoke tests | iPad: device reset flow (Reset Local Data) | Request > approve > code entry. Re-test after the OTP change. | Project-specific | Not started
41 | E. Functional smoke tests | Web My Schedule: Agenda, Week, Month, Map | Click a call: report opens; Week grid drag-and-drop, slot click, right-click menu, Time Off and holiday flags; Manager/Admin Region > Territory > KAM picker. | Project-specific | Not started
42 | E. Functional smoke tests | Account Plans: open a plan and add goal, stakeholder, strategy, team member, action item | These four create methods were missing in devorg1 once; confirm they exist in production. | Project-specific | Not started
43 | E. Functional smoke tests | Support: raise an unlock request and unlock a submitted call; unlock a monthly plan | The unlock flag in SupportUnlockService must be present (CallReportLockService blocks the update otherwise). | Project-specific | Not started
44 | E. Functional smoke tests | Territory: add an HCP to a territory, DCR approval, unassign | Inactive users are skipped by the sharing services; INSUFFICIENT_ACCESS deferral works. | Project-specific | Not started
45 | E. Functional smoke tests | CMS / CLM: push a test document and remove it | Presentation, Slide and Approved_Content created; files removed cleanly. The CMS can re-push removed files - remove at source too. | Project-specific | Not started
46 | E. Functional smoke tests | Reports module (Sciagen Reports): each report per role | KAM own, Manager team, Business Admin all; segment (V1/V2/V3), sales and samples. | Project-specific | Not started
47 | E. Functional smoke tests | Sent email: send one test email from a rep | Needs Email Deliverability set correctly. | Project-specific | Not started
48 | E. Functional smoke tests | Team-schedule API: me, kams, calls, accounts, account-activity | As a Manager and as a KAM (KAM must get 403 on team data). Check paging with limit/offset/afterId. | Project-specific | Not started
49 | E. Functional smoke tests | Update training document and README for what is live | Sales Rep Training Scenarios PDF, Sciagen_Reports_README. | General | Not started
50 | F. Monitoring (first 24-72 hours) | Watch Sync_Tracking__c where Status = Failed, per user | Known past causes: required Member_Name__c missing, Rep__c longer than 18 characters, missing FLS. | Project-specific | Not started
51 | F. Monitoring (first 24-72 hours) | Review Login History for the iPad app and MFA prompts | Remote Access 2.0 logins should be Success. | General | Not started
52 | F. Monitoring (first 24-72 hours) | Review Apex exception emails and debug logs | UNABLE_TO_LOCK_ROW, INSUFFICIENT_ACCESS, sharing and callout errors. | General | Not started
53 | F. Monitoring (first 24-72 hours) | Check scheduled and batch job status | Setup > Apex Jobs, Scheduled Jobs. | General | Not started
54 | F. Monitoring (first 24-72 hours) | Watch API request and storage limits | Sync is chatty; check daily API usage and data/file storage. | General | Not started
55 | F. Monitoring (first 24-72 hours) | Triage the Help & Support inbox | Answer unlock and sync requests promptly in the first days. | General | Not started
56 | G. Rollback and handover | Rollback plan agreed | Redeploy the pre-deployment backup + destructive changes. List data changes that cannot be rolled back. | General | Not started
57 | G. Rollback and handover | Release notes sent to users and the iPad team | What changed, who is affected, known limitations. | General | Not started
58 | G. Rollback and handover | Commit the final state to git and tag the release | The repo must match production after release. | General | Not started
59 | G. Rollback and handover | Sign-off record | Who tested which role, with date; link to deployment ID. | General | Not started

## Summary
Progress summary
All figures are formulas over the Checklist sheet - they update as you change Status.
Phase | Total | Done | In progress | Blocked | Not started | N/A | % complete
A. Pre-deployment gate
B. Immediately after deploy
C. Org settings (not in deployment)
D. Access verification (per role)
E. Functional smoke tests
F. Monitoring (first 24-72 hours)
G. Rollback and handover
Total
Project-specific items still open
Blocked items
Ready to deploy?

## Legend
How to use this workbook
Where to type | Only the yellow columns on the Checklist sheet: Status (pick from the list), Owner, Date done, Notes. Everything else is reference text.
Status values | Not started, In progress, Done, Blocked, N/A. Summary counts them automatically; "N/A" items are left out of the % complete.
Type | "Project-specific" (red) = an issue or decision that came from this project (devorg1 / Int / iPad sync). "General" = standard Salesforce release hygiene.
Order | Work phase A before deploying, B-C immediately after, D-E to verify, F during the first 72 hours, G to close out.
Gate | Summary shows "Gate A complete" only when every phase A item is Done or N/A and nothing is Blocked.
Source | Compiled from the devorg1 / Int comparison, the Int deployment, the coverage and test run (665 tests, 664 passing, all 173 classes at or above 80%), and the sync and access issues fixed during this project (25 Oct 2026).
Open item you should know about | DeviceResetVerifyApiTest.repPermissionSetCannotReadTheCode fails on purpose until the iPad app uses the device-reset verify endpoint and the OTP field access is removed from rep profiles.
Example of a filled row | Status = Done ¦ Owner = A. Kumar ¦ Date done = 27-Oct-2026 ¦ Notes = Validated deploy ID 0AfXX0000000123, 0 failures.